## Bharti+L2VPN
Mantis Bug Tracker Report as on 16.11.2017
Sl.No. | ID | Project | Reporter | Assigned To | Priority | Severity | Date Submitted | Updated | Summary | Status | Resolution
1 | 1056 | Bharti L2VPN | mansi | naveen | normal | minor | 2017-11-16 | 2017-11-16 | l2vpn Src-> If we change intf id to blank it shows error but while dry run it commits successfully. | closed | fixed
2 | 1052 | Bharti L2VPN | mansi | naveen | normal | minor | 2017-11-16 | 2017-11-16 | choice name->after selecting null from drop down and committing successfully,again edit the vpn it will not show the null value. | closed | fixed
3 | 1061 | Bharti L2VPN | satish | naveen | low | minor | 2017-11-16 | 2017-11-16 | L2VPN ¦ Validation Error | closed | fixed
4 | 1047 | Bharti L2VPN | satish | naveen | immediate | block | 2017-11-16 | 2017-11-16 | L2VPN ¦ Unable to Create Dual NPE in Destination | closed | fixed
5 | 1044 | Bharti L2VPN | satish | naveen | high | major | 2017-11-16 | 2017-11-16 | L2VPN ¦ Showing Error While Adding DESTN-NPE | closed | fixed
6 | 1040 | Bharti L2VPN | satish | naveen | low | text | 2017-11-16 | 2017-11-16 | L2VPN ¦ Change Title | closed | fixed
7 | 1038 | Bharti L2VPN | satish | naveen | normal | minor | 2017-11-16 | 2017-11-16 | L2VPN ¦ L2vpn No-Autoneg Speed (SRC & DESTN) | closed | fixed
8 | 1062 | Bharti L2VPN | satish | naveen | low | minor | 2017-11-16 | 2017-11-16 | L2VPN ¦ Validation Error | closed | fixed
9 | 1050 | Bharti L2VPN | rajasekhar | naveen | normal | minor | 2017-11-16 | 2017-11-16 | L2VPN - MTU - Default Value | closed | fixed
10 | 1049 | Bharti L2VPN | rajasekhar | naveen | high | major | 2017-11-16 | 2017-11-16 | Add an ACC-NPE intra-CEN, Dual NPE, BW < 500Mbps, w/ VLAN Tag L2vpn Link | closed | fixed
11 | 1048 | Bharti L2VPN | rajasekhar | naveen | high | minor | 2017-11-16 | 2017-11-16 | L2VPN ¦ Primary-pwid | closed | fixed
12 | 1046 | Bharti L2VPN | rajasekhar | naveen | normal | minor | 2017-11-16 | 2017-11-16 | L2VPN ¦ Last-mile - NPE devices. | closed | fixed
13 | 1045 | Bharti L2VPN | rajasekhar | naveen | normal | minor | 2017-11-16 | 2017-11-16 | L2VPN ¦ Destn - Protocols values not showing | closed | fixed
14 | 1042 | Bharti L2VPN | rajasekhar | naveen | normal | minor | 2017-11-16 | 2017-11-16 | L2VPN ¦ Discard changes Issue. | closed | fixed
15 | 1055 | Bharti L2VPN | rajasekhar | naveen | high | major | 2017-11-16 | 2017-11-16 | L2VPN Add an ACC-NPE intra-CEN, Dual NPE, BW < 500Mbps, w/ VLAN Tag L2vpn Link | closed | fixed
16 | 1054 | Bharti L2VPN | rajasekhar | naveen | high | major | 2017-11-16 | 2017-11-16 | L2VPN - ACC-ACC - Inter CEN - BW < 500 Mbps | closed | fixed
17 | 1053 | Bharti L2VPN | rajasekhar | naveen | high | major | 2017-11-16 | 2017-11-16 | L2VPN - Add an ACC-NPE intra-CEN, Single Agg-Single NPE, BW > 500Mbps L2vpn Link | closed | fixed
18 | 1051 | Bharti L2VPN | rajasekhar | naveen | normal | minor | 2017-11-16 | 2017-11-16 | L2VPN - VPN Name (ckt-id) | closed | fixed
19 | 1041 | Bharti L2VPN | rajasekhar | naveen | high | major | 2017-11-16 | 2017-11-16 | L2VPN ¦ Customer Name is mandatory in YANG Module | closed | fixed
20 | 1037 | Bharti L2VPN | rajasekhar | naveen | high | major | 2017-11-16 | 2017-11-16 | L2VPN ¦ Bandwidth is mandatory in YANG Module | closed | fixed
21 | 1034 | Bharti L2VPN | rajasekhar | naveen | high | minor | 2017-11-16 | 2017-11-16 | L2VPN ¦ Protocols - Selected protocol is not showing. | closed | fixed
22 | 1029 | Bharti L2VPN | rajasekhar | naveen | normal | minor | 2017-11-16 | 2017-11-16 | L2VPN - Src - Vlan-id | closed | fixed
23 | 1031 | Bharti L2VPN | sonia | sonia | normal | minor | 2017-11-16 | 2017-11-16 | L2 ¦ Calender date must be autoselected as todays date(client requirement) | closed | fixed
24 | 1035 | Bharti L2VPN | sonia | sonia | normal | minor | 2017-11-16 | 2017-11-16 | L2 ¦ Close button not required | closed | fixed
25 | 1036 | Bharti L2VPN | sonia | sonia | normal | minor | 2017-11-16 | 2017-11-16 | L2 ¦ Error message grammer correction | closed | fixed
26 | 1043 | Bharti L2VPN | sonia | sonia | normal | minor | 2017-11-16 | 2017-11-16 | L2 ¦ Dryrun error ¦ Dryrun window is displaying some other content | closed | fixed
27 | 1039 | Bharti L2VPN | sonia | sonia | normal | major | 2017-11-16 | 2017-11-16 | L2 ¦ Error while adding dual devices | closed | fixed
28 | 1033 | Bharti L2VPN | sonia | sonia | normal | minor | 2017-11-16 | 2017-11-16 | L2 ¦ Standardization | closed | fixed
29 | 1030 | Bharti L2VPN | sonia | sonia | normal | minor | 2017-11-16 | 2017-11-16 | L2 ¦ Devices Title should be corrected in destination lag | closed | fixed