## Bharti+L2VPN
Sl.No | Re-Test | Bug ID | Reporter | Assigned To | Severity | Date Submitted | Updated | Summary | Status | Resolution
1 | Updated Notes in Mantis | 1089 | stuti | naveen | minor | 2017-11-24 | 2017-11-24 | Wrong Interface ID shows no change in vpn or commits with the last valid value entered | assigned | open
2 | Updated Notes in Mantis | 1090 | stuti | naveen | minor | 2017-11-24 | 2017-11-24 | Bandwidth if modified and set to Null should show an error on committing the service instead of showing 'no change in vpn" | feedback | open
3 | Updated Notes in Mantis | 1079 | stuti | naveen | minor | 2017-11-21 | 2017-11-23 | L2vpn page taking too long to download | assigned | open
4 | PASS | 1077 | stuti | naveen | minor | 2017-11-21 | 2017-11-22 | Device dropdown in every container should show only relevant set of devices according to the role. | resolved | fixed
5 | PASS | 1078 | stuti | naveen | minor | 2017-11-21 | 2017-11-22 | Search option should be available for device dropdown | resolved | fixed
6 | PASS | 1080 | stuti | naveen | minor | 2017-11-21 | 2017-11-22 | Got error " Some issue occured please check the value" | resolved | fixed
7 | PASS | 1081 | stuti | naveen | feature | 2017-11-21 | 2017-11-22 | Device deletion should invoke a confirmation pop up window. | resolved | fixed
8 | PASS | 1082 | stuti | naveen | minor | 2017-11-21 | 2017-11-22 | Not accepting vlan id 1 under evc | resolved | fixed
9 | Updated Notes in Mantis | 1076 | stuti | naveen | minor | 2017-11-21 | 2017-11-22 | Unable to modify service choice from business/mobility/dslam to blank without deleting type | resolved | fixed
10 | PASS | 1068 | stuti | naveen | minor | 2017-11-21 | 2017-11-21 | Selected protocols in l2protocol container should be shown as checked | closed | fixed
11 | PASS | 1067 | stuti | naveen | minor | 2017-11-21 | 2017-11-21 | Service options should be a dropdown | closed | fixed
12 | PASS | 1063 | stuti | naveen | major | 2017-11-17 | 2017-11-17 | Unable to view options after MTU on UI | resolved | fixed